## TestPlan ScreenReader
Test Planner and Tracker |  |  | ProjectName
Remove sample items before submitting this.
Test No. ID | Trace to User Story ID and Name | Pre-conditions | Test Description (steps) | Expected Outcome | Sprint 1Outcome | Sprint 2 Outcome | Sprint 3 Outcome
1 | Screen reader reads blocks correctly | 1.Workspace active 2.Blocks are in workspace | 1.Select each block. 2.Listen to the block and any dropdown menus it may have. | Everything on the block is read. Including input blocks
2 | When block is added screen reader doesn't continue reading toolbox | 1.Workspace active 2.Toolbox closed | 1.Add a new block to the workspace. 2.Listen to the new block. | Only the new block is read.
3 | Screen reader only reads when prompted by user to continue | 1.Workspace active | 1.Connect several blocks together. 2.Select the top block. 3.Listen to the block | Only the selected block is read
4 | Blocks make sense audibly | 1.Workspace active 2.Blocks are in workspace | 1.Listen to each block. 2.Question whether what is read is understandable. | Blocks purpose and content should be clear with no ambiguity and accurately represent what the blocks are.
5 | Keystrokes don't interfere with screenreader | 1.Have screen reader and blockly open 2.Be familiar with the screenreaders hotkeys | 1.Use the screen readers default hotkeys to navigate the page 2.Test out each hotkey while using a screen reader. | All screen reader hotkeys work without issues and blockly's hotkeys do not trigger any screen reader events
6 | User knows audibly where they are on the page | Open/show call out block | 1.Move around the page. 2.Press the info key to find out where you are on the page | If in the code read the info box. Otherwise re-read selection.
7
8 |  |  |  |  | Code red if it does not work
9 |  |  |  |  | Code green if it passes completely
10 |  |  |  |  | Code yellow if partially with note on issue
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29

## Test Cases - Black Box
Test Case ID | Area | Description | Requirements Trace | Directions | Expected Output | Priority | Status
TC-AUTH-001 | Authentication | Sign up with valid credentials | AUTH-001 | Open app → Auth page → Fill valid email/password → Create account. | User account created; redirected to Editorial page; session cookie/token set. | High | Planned
TC-AUTH-002 | Authentication | Sign in existing user | AUTH-002 | Open app → Auth page → Enter valid credentials → Sign in. | Redirect to Editorial; session active; user name visible. | High | Planned
TC-AUTH-003 | Authentication | Reject invalid password policy | AUTH-003 | Attempt sign up with weak password. | Inline validation shows policy error; account not created. | Medium | Planned
TC-AUTH-004 | Authentication | Sign out clears session | AUTH-004 | From Editorial, choose Sign out. | Returned to Auth page; accessing Editorial requires re-auth. | High | Planned
TC-AUTH-005 | Authentication | Session expiry/refresh | AUTH-005 | After token expiry simulate API call. | Silent refresh works or user is prompted to sign in again. | Medium | Planned
TC-EDIT-001 | Editorial | Create new résumé | EDIT-001 | From Editorial, click New → enter headline and first section. | Draft created with untitled name; auto-save enabled. | High | Planned
TC-EDIT-002 | Editorial | Edit and save content | EDIT-002 | Modify a line; pause 1–2s. | Auto-save to Azure backend; save indicator confirms. | High | Planned
TC-EDIT-003 | Editorial | Reload restores content | EDIT-003 | Hard refresh browser. | All content restored from backend; caret position reasonable. | High | Planned
TC-EDIT-004 | Editorial | Undo/redo editing | EDIT-004 | Make changes then undo/redo. | Edits revert/restore without data loss. | Medium | Planned
TC-EDIT-005 | Editorial | Unauthorized access blocked | SEC-002 | Open /editorial route while signed out. | Redirected to Auth; 401/403 on protected APIs. | High | Planned
TC-CHAT-001 | Inline Chat | Request suggestions for a line | CHAT-001 | Select a résumé line → Click 'Ask AI'. | Chat panel opens with suggestions contextual to selected line. | High | Planned
TC-CHAT-002 | Inline Chat | Apply suggestion | CHAT-002 | Click 'Apply'. | Line text updates; change is auto-saved. | High | Planned
TC-CHAT-003 | Inline Chat | Rate/undo suggestion | CHAT-003 | Rate suggestion or undo. | Feedback recorded; content reverts if undone. | Medium | Planned
TC-CHAT-004 | Inline Chat | Error/timeout handling | CHAT-004 | Simulate API error or slow response. | Non-blocking error; retry option; editor remains usable. | High | Planned
TC-CHAT-005 | Inline Chat | Quota exceeded scenario | CHAT-005 | Simulate quota cap. | Graceful degradation message; prevents repeated calls within cooldown. | Medium | Planned
TC-AZ-001 | Azure Backend | Create/read/update résumé via API | AZ-CRUD-001 | Use app to create and edit; observe network. | 200 responses; persisted data consistent with UI. | High | Planned
TC-AZ-002 | Azure Backend | Handle network loss | AZ-RES-002 | Toggle offline mid-edit. | Changes queued; user warned; sync resumes on reconnect. | High | Planned
TC-AZ-003 | Azure Backend | Authorization on APIs | SEC-API-003 | Call APIs without token. | 401/403; no data leaked. | High | Planned
TC-AZ-004 | Azure Backend | Data model validation | AZ-VAL-004 | Post malformed payload via API test client. | 400 with clear validation errors; no server crash. | Medium | Planned
TC-AZ-005 | Azure Backend | Basic performance smoke | PERF-005 | Measure p95 for save and chat relay. | p95 save < 800ms; chat relay < 2.5s (targets). | Medium | Planned

## Test Cases - White Box
Test Case ID | Area | Description | Directions/Goals | Expected Output | Priority | Status
TC-WB-001 | Auth | Auth guard unit tests | Simulate routes with/without tokens; token refresh edge cases. | Correct redirects; refresh paths covered. | High | Planned
TC-WB-002 | Editor | Editor reducers/selectors | Fuzz edits, undo/redo, autosave triggers. | Deterministic state; no orphan timers. | Medium | Planned
TC-WB-003 | Chat | Chat adapter | Mock chat service; test retries/backoff and cancellation. | Retries bounded; cancellation respected. | Medium | Planned
TC-WB-004 | API | API client | Mock Azure endpoints; validate error mapping. | Consistent error objects; no unhandled rejections. | Medium | Planned
TC-WB-005 | Accessibility | Accessibility unit checks | Snapshot tests for aria-* attributes and labels. | All interactive controls labeled; focus traps avoided. | Low | Planned

## Risks
# | Risk | Impact | Trigger | Mitigation Plan
1 | Scope creep as functionality becomes clearer | High | Backlog growth mid-sprint | Enforce definition-of-done; freeze scope after planning; defer to Sprint 3.
2 | External dependency on Azure services | Medium | Regional outage / rate limiting | Retries/backoff; circuit breakers; local mock server.
3 | Auth integration issues (token expiry, CORS) | Medium | 401/403 spikes in QA | Token refresh and CORS tests in CI; monitor; fallback to logout.
4 | Chat cost/latency variability | Medium | High p95 latency or quota exceeded | Cache identical prompts; non-blocking UI; limit retries; quota watch.
5 | Accessibility regressions on new pages | Low | Keyboard traps / missing labels | axe-core scan in CI; manual keyboard walkthrough; fix before merge.

## Schedule
Task Name | Start | Finish | Effort | Comments
Test Planning | Oct 16, 2025 | Oct 17, 2025 | 1d | Identify AC and risks.
Review Requirements | Oct 16, 2025 | Oct 18, 2025 | 2d | Trace stories AUTH/EDIT/CHAT/AZ-*.
Create initial test estimates | Oct 18, 2025 | Oct 18, 2025 | 0.5d | Coverage & automation split.
Learn new test resources | Oct 18, 2025 | Oct 20, 2025 | 2d | Playwright setup; API fixtures.
First deploy to QA | Oct 21, 2025 | Oct 21, 2025 | 0.5d | Smoke & env checks.
Functional testing – Sprint 2 | Oct 21, 2025 | Oct 31, 2025 | 7d | Black-box story tests.
Iteration 2 deploy to QA | Oct 28, 2025 | Oct 28, 2025 | 0.5d | Mid-sprint fixes.
System testing | Nov 1, 2025 | Nov 2, 2025 | 2d | End-to-end flows across features.
Regression testing | Nov 2, 2025 | Nov 3, 2025 | 1d | Sprint 1 surfaces touched by changes.
Usability Testing | Nov 3, 2025 | Nov 3, 2025 | 0.5d | Editorial & chat UX walk-through.
Resolution of final defects & final build testing | Nov 3, 2025 | Nov 4, 2025 | 1d | Close P1/P2s.
Deploy to Staging | Nov 4, 2025 | Nov 4, 2025 | 0.5d | Go/no-go checklist.
Performance testing (smoke) | Nov 4, 2025 | Nov 4, 2025 | 0.5d | p95 save/chat targets.
Sprint 2 Demo / Release | Nov 5, 2025 | Nov 5, 2025 | 0.5d | Stakeholder demo.

## Deliverables
Deliverable
Updated test plan & traceability to Sprint 2 stories
Automated test suites: unit, API, E2E (CI artifacts)
Test summary report with defect list and pass/fail status
Accessibility and performance smoke results

## Assumptions
Assumption
Azure resources are provisioned and reachable from test networks.
Env vars/flags allow pointing the web app at QA/Staging backends.
Inline chat model/endpoint is stable with configured quotas.
Test accounts and seed data are available.